X Public Library Strategic Plan

Work Plan

20xx-20xx

# **GOAL 1**

**The library will provide in-person opportunities for people to interact with each other.**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Goal | Activity | Time Frame | Staff Involved | Resources Needed | Outcomes | Progress |
| 1 | Board game night | September-November 20xx (monthly) | Library Assistant | Board games; Staff time (2 hours per month); $30 per month for snacks and beverages | Increase in the number of people coming to the library for programs.  Feedback from community members about how much they enjoy connecting with each other | First event held September 20; 15 in attendance; 100% positive feedback and said they would attend again |
| 1 | Themed community potlucks | October 15 | Library Director, Library Assistant | Meeting Room; Staff time (4 hours per month); fliers |  | Scheduled for October 15 |
| 1 | Programs for seniors | November 20xx-April 20xx (monthly) | Librarian | Meeting room; Staff time (2 hours per month); volunteer time |  | Not yet started |
| 1 | Trivia Night | January-May 20xx | Librarian | Staff time; meeting space at local brewery |  | Not yet started |
| 1 | Bingo Night at the Library | TBD |  |  |  | Not yet started |