X Public Library Strategic Plan

Work Plan

20xx-20xx

# **GOAL 1**

**The library will provide in-person opportunities for people to interact with each other.**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Goal | Activity | Time Frame | Staff Involved | Resources Needed | Outcomes | Progress |
| 1   | Board game night  | September-November 20xx (monthly)  | Library Assistant  | Board games; Staff time (2 hours per month); $30 per month for snacks and beverages  | Increase in the number of people coming to the library for programs.  Feedback from community members about how much they enjoy connecting with each other  | First event held September 20; 15 in attendance; 100% positive feedback and said they would attend again  |
| 1   | Themed community potlucks  | October 15  | Library Director, Library Assistant  | Meeting Room; Staff time (4 hours per month); fliers  |  | Scheduled for October 15  |
| 1   | Programs for seniors  | November 20xx-April 20xx (monthly)  | Librarian  | Meeting room; Staff time (2 hours per month); volunteer time  |  | Not yet started  |
| 1   | Trivia Night  | January-May 20xx  | Librarian  | Staff time; meeting space at local brewery  |  | Not yet started  |
| 1   | Bingo Night at the Library  | TBD  |   |   |  | Not yet started  |